## E2E_Time_Frame
Estimated time per Scenarios for Topology 1
Strategy: | The strategy is to test the main functionalities of iMentor in a testing environment.
Target Date: | We expect to achieve a test coverage in iMentor exceeding 90% in terms of functionalities, buttons, links, user interface display, and how information is presented on it. Some functionalities should not be tested due a shot time to test
FEB
[6 empty] | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 28 | 26 | 27 | 28
Start Date | EndDate | #Days / #QEs | Task | Status | Comments | FEB 9: F; FEB 12: M; FEB 13: T; FEB 14: w; FEB 15: T; FEB 16: F; FEB 19: M; FEB 20: T
2023-02-09 | 2023-02-14 | 2 QEs | Exploratory test | ON TRACK | We finished the exploratory test and get enough knowledge about imentor | bar: FEB 9 to FEB 14
2023-02-13 | 2023-02-16 | 2 QEs | High-level test cases created | ON TRACK | 17 high-level test cases were created | bar: FEB 9; FEB 13 to FEB 16
2023-02-15 | 2023-02-28 | 2 QEs | Test plan creation | COMPLETED | The test plan was created and finished
2023-02-17 | 2023-02-28 | 2 QEs | Low-level test cases creation | COMPLETED | At the end a 150 tc were created | bar: FEB 17 to FEB 28
List of scenarios:
Scenario1: Happy path ¦ Mentor ¦ Student
Scenario 2: Error handling ¦ Sign in ¦ Sign up
Scenario 3: Functionalities ¦ Student ¦ Mentor
Scenario 4: Update data ¦ Account ¦ Course

## OVERVIEW
Test: iMentor
Current Status: | In-Progress | 98.03%
Test Summary
|  |  | iMentor test summary |  |  | Bugs summary
|  |  | . | # | % | . | # | %
|  |  | Total Tests | 152 | 100% | Total Bugs reported | 47 | 100%
|  |  | Tests Executed | 149 | 98.03% | Open | 7 | 14.89%
|  |  | Passed | 131 | 86.18% | In progress | 6 | 12.77%
|  |  | Failed | 15 | 9.868% | Closed | 1 | 2.128%
|  |  | In Progress | 0 | 0% | Critical | 0 | 0%
|  |  | Blocked | 3 | 1.974% | High | 6 | 12.77%
|  |  | On Hold | 0 | 0% | Medium | 16 | 34.04%
|  |  | Tests Not Executed | 3 | 1.974% | Low | 25 | 53.19%
Basic Info ¦ Project Team |  |  | Graphs related to Bugs submitted
OM
PM | Eduardo Espinoza
Architects
Dev Managers
Qa Lead | Mauricio Zelaya
Dev Team | Dev team
QE Tasks
Dates | Start Date | End Date
Test Plan Creation | 2023-02-15 | 2023-02-28
Test Plan Review and Updates | 2023-02-23 | 2023-02-28
Test Plan Refinement | 2023-02-24 | 2023-02-28
E2E Testing | 2023-02-13
History
Change Log | Date | Who made the changes
Started document | 2023-02-15 | QE Team
Writting test cases | 2023-02-13 | QE Team

## HLTCS_UI
Test Cases Tracking - iMentor
[8 empty] | Execution % | Execution % | Execution %
ORDERING AND PROVISIONING | [7 empty] | 43.42% | 69.74% | 96.0526
# | ID | Tester | Description | Priority | Type | Type2 | Validations | Execution 1 Status | Execution 2 Status | Execution 3 Status | Smoke | Regression | Comments
1 | TD01-12 |  | Home page > Verify that all buttons are working (specific redirect) | Medium | Acceptance | Positive |  | Passed | Passed | Passed | Yes | Yes
2 | TD01-15 |  | Home > Navigation verification (compatibility web browsers) | Medium | Acceptance |  |  | Passed | Passed | Passed | Yes | Yes
3 | TD01-502 |  | Home page > Verify that the 'Become a mentor' button is not displayed when a mentor logs in | Low | Functional |  |  | Passed | Passed | Passed | No | No
4 | TD01-400 |  | Home page > Verify that publication can be search | Medium | Functional |  |  | Passed | Passed | Passed | Yes | Yes
5 | TD01-21 |  | Sign up > Verify that the sign up form is accessible | High | Acceptance |  |  | Passed | Passed | Passed | Yes | Yes
6 | TD01-23 |  | Sign up > Verify that mandatory fields are clearly marked in Sign Up form | Low | Acceptance |  |  | Passed | Passed | Passed | yes | No
7 | TD01-26 |  | Sign up > Validate valid input data | Medium | Functional | Positive |  | Passed | Passed | Passed | No | No
8 | TD01-30 |  | Sign up > Test form submission | High | Functional |  |  | Passed | Passed | Passed | yes | yes
9 | TD01-39 |  | Sign up > Check password strength requirements | Low | Non-Functional |  |  | Not executed | Not executed | Not executed | No | No
10 | TD01-346 |  | Sign up > Verify after filling all mandatory fields with valid data can be created a new account. | Medium | Acceptance | Positive |  | Passed | Passed | Passed | yes | yes
11 | TD01-633 |  | Sign up > Data validation, invalid data | Medium | Acceptance | Negative |  | Passed | Passed | Passed | No | yes
12 | TD01-385 |  | Sign Up > Verify that can be created a new user account by API | High | Functional | Domain |  | Not executed | Not executed | Not executed | No | No
13 | TD01-83 |  | Sign in > Verify that the sign in form is accessible. | Medium | Acceptance |  |  | Passed | Passed | Passed | yes | yes
14 | TD01-85 |  | Sign in > Check required fields. | Low | Acceptance |  |  | Passed | Passed | Passed | No | No
15 | TD01-87 |  | Sign in > Test password authentication. | High | Acceptance | Positive |  | Passed | Passed | Passed | Yes | Yes
16 | TD01-88 |  | Sign in > Test users can log in with Facebook. | Medium | Acceptance |  |  | Not executed | Not executed | Failed | No | yes
17 | TD01-92 |  | Sign in > Test users can log in with Google. | Medium | Acceptance |  |  | Not executed | Not executed | Failed | No | yes
18 | TD01-95 |  | Sign in > Forgot password link. | High | Functional |  |  | Passed | Passed | Passed | Yes | Yes
19 | TD01-432 |  | Sign in > Verify that users can't access using invalid credentials. | High | Functional | Negative |  | Passed | Passed | Passed | No | Yes
20 | TD01-434 |  | Sign in > Verify that users can't access with blank user and password. | Medium | Functional | Negative |  | Passed | Passed | Passed | No | yes
21 | TD01-333 |  | Profile > General information fields | Medium | Acceptance |  |  | Passed | Passed | Passed | yes | no
22 | TD01-334 |  | Profile > Valid social links. | Low | Acceptance | positive |  | Passed | Passed | Passed | No | No
23 | TD01-335 |  | Profile > Invalid social links. | Low | acceptance | negative |  | Failed | Failed | Failed | No | No
24 | TD01-347 |  | General Profile > Verify if mapbox can saves ubications by clicking Save changes button. | Low | Functional |  |  | Passed | Passed | Passed | No | No
25 | TD01-873 |  | General Profile > Verify if mapbox can searches ubications. | Low | functional |  |  | Passed | Passed | Passed | no | no
26 | TD01-348 |  | General Profile > Verify if languages can be added by clicking "+" button | High | Functional | Acceptance |  | Passed | Passed | Passed | No | No
27 | TD01-350 |  | General Profile > Verify that languages selection can not be saved without any language. | Medium | Negative | Negative |  | Failed | Failed | Failed | No | No
28 | TD01-351 |  | General Profile > Verify that languages stay marked in languages selection. | Low | Functional | Positive |  | Failed | Failed | Failed | No | No
29 | TD01-352 |  | General Profile > Verify that can be added a profile picture by Drag and drop any image file. | Medium | functional |  |  | Passed | Passed | Passed | No | No
30 | TD01-354 |  | General Profile > Verify that can be added a profile picture by browsing a image file. | Medium | Functional |  |  | Passed | Passed | Passed | No | Yes
31 | TD01-356 |  | General Profile > Verify that profile picture can be added from Facebook account. | Low | Functional |  |  | Not executed | Passed | Blocked | No | No
32 | TD01-357 |  | General Profile > Verify that profile picture can be added from Instagram account. | Low |  |  |  | Not executed | Passed | Blocked | No | No
33 | TD01-359 |  | General Profile > Verify that profile picture can be added from Google Drive. | Low | Functional |  |  | Not executed | Not executed | Blocked | No | No
34 | TD01-364 |  | General Profile > Verify that profile picture can be deleted. | Medium |  |  |  | Failed | Failed | Failed | No | No
35 | TD01-368 |  | General Profile > Verify that valid files are accepted as profile picture. | Low | Functional | Positive |  | Passed | Passed | Passed | No | Yes | Cloudinary accepts various types of image files
36 | TD01-369 |  | General Profile > Verify that invalid files are rejected as profile picture. | Medium | Functional | Negative |  | Passed | Passed | Passed | No | Yes | The limit for an image is 2,84MB
37 | TD01-370 |  | General Profile > Verify that full account name is displayed in the left pane below profile picture. | High | Positive | Domain |  | Passed | Passed | Passed | No | No
38 | TD01-371 |  | General Profile > Verify that Profile button in left menu redirects to General Profile page. | High | Functional | Domain |  | Passed | Passed | Passed | No | No
39 | TD01-372 |  | General Profile > Verify that Message button in left menu redirects to Chats page. | High | Functional | Domain |  | Passed | Passed | Passed | No | No
40 | TD01-373 |  | General Profile > Verify that Settings button in left menu redirects to Account Security page. | High | Functional | Domain |  | Passed | Passed | Passed | No | No
41 | TD01-381 |  | General Profile > Settings > Verify that password can be resetted. | High | Functional | Domain |  | Passed | Passed | Passed | No | No
42 | TD01-831 |  | General Profile > Settings > Verify that email can be updated. | Low | Functional | Domain |  | Not executed | Failed | Failed | No | No | Email cant be updated, Email field only saves the email filled when clicked Update button.
43 | TD01-832 |  | General Profile > Settings > Verify that an account can be suspended. | High | Functional |  |  | Passed | Passed | Passed | yes | Yes
44 | TD01-875 |  | General Profile > Settings > Verify that suspended account can be restored. | High | Functional |  |  | Passed | Passed | Passed | Yes | Yes
45 | TD01-833 |  | General Profile > Settings > Verify that an account can be hard deleted. | High | Functional | Domain |  | Not executed | Not executed | Failed | No | No | Email is still registered in iMentor Database, account is not hard deleted.
46 | TD01-834 |  | General Profile > Settings > Delete account > Verify that Cancel button return to previous page | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
47 | TD01-392 |  | General Profile > Verify that email can be verified by API | High | Functional | Domain |  | Not executed | Not executed | Not executed | No | No
48 | TD01-429 |  | Logout > Verify that the user can log out from iMentor | High | Functional |  |  | Passed | Passed | Passed | yes | yes
49 | TD01-431 |  | Logout > Verify that the user can't access with "back" after a successfully log out. | High | Functional | Negative |  | Passed | Passed | Passed | yes | yes
50 | TD01-503 |  | Verify students can log in with their credentials. | High | acceptance | Positive |  | Passed | Passed | Passed | yes | yes
51 | TD01-506 |  | Verify students can request a course | Medium | acceptance |  |  | Passed | Passed | Passed | yes | yes
52 | TD01-508 |  | Verify students can access to their learning dashboard | Medium | acceptance |  |  | Passed | Passed | Passed | No | yes
53 | TD01-513 |  | Verify that the dashboard remains blue when logging in as a student | Low | Functional |  |  | Passed | Passed | Passed | No | No
54 | TD01-544 |  | Verify that students can see published courses | High | acceptance |  |  | Passed | Passed | Passed | yes | yes
55 | TD01-545 |  | Verify that students cannot view courses in unpublished status | Low |  |  |  | Failed | Failed | Failed | No | Yes | During the first executions students were able to see unpublished courses
56 | TD01-505 |  | Verify mentors can log in with their credentials | High | Acceptance | Positive |  | Passed | Passed | Passed | Yes | Yes
57 | TD01-507 |  | Verify mentors can create a course | High | Acceptance |  |  | Passed | Passed | Passed | No | Yes
58 | TD01-509 |  | Verify mentors can access to the mentoring dashboard | High | Acceptance |  |  | Passed | Passed | Passed | yes | yes
59 | TD01-514 |  | Verify that the dashboard is white when logging in as a mentor | Low | Functional |  |  | Passed | Passed | Passed | No | No
60 | TD01-546 |  | Verify that the mentor can see the courses requested by the students | Medium | acceptance |  |  | Passed | Passed | Passed | yes | yes
61 | TD01-547 |  | Become a mentor > Verify that fields and information of Become a mentor form are properly displayed | High | acceptance |  |  | Passed | Passed | Passed | yes | yes
62 | TD01-548 |  | Become a mentor > Verify that Cancel button in Become a mentor form cancels any action and gets back. | High | functional | positive |  | Passed | Passed | Passed | No | No
63 | TD01-549 |  | Become a mentor > Verify if clicking Next button can go forward when filling all mandatory fields. | High | Functional |  |  | Passed | Passed | Passed | No | No
64 | TD01-550 |  | Become a mentor > Verify if clicking Next button can't go forward when mandatory fields are empty. | High | Functional | negative |  | Passed | Passed | Passed | No | No
65 | TD01-628 |  | Become a mentor >Verify if can be selected a country by clicking "Choose your country" dropdown list | High | acceptance |  |  | Passed | Passed | Passed | No | No
66 | TD01-630 |  | Become a mentor >Verify if a language can be picked by clicking "Choose your language" dropdown list | High | acceptance |  |  | Passed | Passed | Passed | No | No
67 | TD01-631 |  | Become a mentor > Verify if Education/Studies field accepts 45 characters. | Low | Functional | positive |  | Not executed | Not executed | Passed | No | No
68 | TD01-632 |  | Become a mentor > Verify if Education/Studies field accepts 46 characters. | Low | Functional | negative |  | Not executed | Not executed | Passed | No | No
69 | TD01-635 |  | Become a mentor > Verify if Education/Studies field accepts 1 character. | Low | Functional | negative |  | Not executed | Not executed | Passed | No | No
70 | TD01-636 |  | Become a mentor > Verify if Profession field accepts 1 character. | Low | Functional | Negative |  | Not executed | Not executed | Passed | No | No
71 | TD01-637 |  | Become a mentor > Verify if Description field accepts 19 characters. | Low | Functional | Positive |  | Not executed | Not executed | Passed | No | No
72 | TD01-638 |  | Become a mentor > Verify if Description field accepts 20 characters. | Low | functional | positive |  | Not executed | Not executed | Passed | No | No
73 | TD01-639 |  | Become a mentor > Verify if Description field accepts 1000 characters | Low | functional | positive |  | Not executed | Not executed | Passed | No | No
74 | TD01-640 |  | Become a mentor > Verify if Description field accepts 1001 characters | Low | functional | negative |  | Not executed | Not executed | Passed | No | No
75 | TD01-641 |  | Become a mentor > Verify if Profession field accepts 150 characters. | Low | functional | positive |  | Not executed | Not executed | Passed | No | No
76 | TD01-642 |  | Become a mentor > Verify if Profession field accepts 151 characters. | Low | functional | negative |  | Not executed | Passed | Passed | No | No
77 | TD01-643 |  | Become a mentor >Verify if a Mentor request can be submitted with empty fields in Course Information. | Medium | functional | negative |  | Passed | Passed | Passed | No | No
78 | TD01-644 |  | Become a mentor > Verify if Course title field accepts 10 characters. | Low | functional | positive |  | Not executed | Not executed | Passed | No | No
79 | TD01-645 |  | Become a mentor > Verify if Course title field accepts 150 characters. | Low | functional | positive |  | Not executed | Not executed | Passed | No | No
80 | TD01-874 |  | Become a mentor > Verify if Course title field doesnt accept 9 characters. | Low | functional | negative |  | Not executed | Not executed | Passed
81 | TD01-646 |  | Become a mentor > Verify if Course title field doesnt accept 151 characters. | Low | functional | negative |  | Not executed | Passed | Passed | No | No
82 | TD01-647 |  | Become a mentor > Verify if Course Description field doesnt accept 19 characters. | Low | functional | negative |  | Not executed | Passed | Passed | No | No
83 | TD01-648 |  | Become a mentor > Verify if Course Description field accepts 20 characters. | Low | functional | positive |  | Not executed | Not executed | Passed | No | No
84 | TD01-649 |  | Become a mentor > Verify if Course Description field accepts 1000 characters. | Low | functional | Positive |  | Not executed | Not executed | Passed | No | No
85 | TD01-650 |  | Become a mentor > Verify if Course Description field doesnt accept 1001 characters. | Low | functional | Negative |  | Not executed | Passed | Passed | No | No
86 | TD01-651 |  | Become a mentor > Verify that is displayed a confirmation message after submitting a mentor form. | High | acceptane |  |  | Not executed | Passed | Passed | No | No
87 | TD01-652 |  | Become a mentor > Verify if Dashboard button changes its color when hover over it. | Low | functional |  |  | Passed | Passed | Passed | No | No
88 | TD01-653 |  | Become a mentor >Verify if Dashboard button in confirmation message redirects to Mentoring Dashboard. | High | functional |  |  | Passed | Passed | Passed | No | No
89 | TD01-657 |  | Verify that Balance button redirects to balance page as Mentor | Medium | Functional | Domain |  | Passed | Passed | Passed | No | No
90 | TD01-659 |  | Verify that can be added a new professional profile. | Medium | Functional | Domain |  | Passed | Passed | Passed | No | No
91 | TD01-660 |  | Verify that can be edited a Professional profile. | Medium | Functional | Domain |  | Passed | Passed | Passed | No | No
92 | TD01-661 |  | Professional Profile > Verify if Certifications or Diplomas can be added. | Medium | Functional | Domain |  | Not executed | Passed | Passed | No | No
93 | TD01-662 |  | Professional Profile > Verify if Certifications or Diplomas can be added with empty fields. | Medium | Negative | Domain |  | Not executed | Passed | Passed | No | No
94 | TD01-663 |  | Professional Profile > Certifications and Diplomas > Verify if Name field accepts 5 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
95 | TD01-664 |  | Professional Profile > Certifications and Diplomas > Verify if Name field doesnt accept 4 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
96 | TD01-665 |  | Professional Profile > Certifications and Diplomas > Verify if Name field accepts 50 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
97 | TD01-666 |  | Professional Profile > Certifications and Diplomas > Verify if Name field doesnt accept 51 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
98 | TD01-667 |  | Professional Profile > Certifications and Diplomas > Verify if Issuer field accepts 5 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
99 | TD01-668 |  | Professional Profile > Certifications and Diplomas > Verify if Issuer field accepts 50 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
100 | TD01-669 |  | Professional Profile > Certifications and Diplomas > Verify if Issuer field doesnt accept 4 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
101 | TD01-670 |  | Professional Profile > Certifications and Diplomas > Verify if Issuer field doesnt accept 51 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
102 | TD01-671 |  | Professional Profile > Verify if Certifications and Diplomas can be deleted. | Medium | Functional | Domain |  | Not executed | Passed | Passed | No | No
103 | TD01-672 |  | Professional Profile > Verify that can be added a Work experience. | Medium | Functional | Domain |  | Not executed | Passed | Passed | No | No
104 | TD01-673 |  | Professional Profile > Verify that can be added a Work experience with empty fields. | Medium | Negative | Domain |  | Not executed | Passed | Passed | No | No
105 | TD01-674 |  | Professional Profile > Work Experience > Verify if Title field accepts 5 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
106 | TD01-675 |  | Professional Profile > Work Experience > Verify if Title field accepts 50 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
107 | TD01-676 |  | Professional Profile > Work Experience > Verify if Title field doesnt accept 4 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
108 | TD01-677 |  | Professional Profile > Work Experience > Verify if Title field doesnt accept 51 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
109 | TD01-678 |  | Professional Profile > Work Experience > Verify if Company field accepts 5 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
110 | TD01-679 |  | Professional Profile > Work Experience > Verify if Company field accepts 50 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
111 | TD01-680 |  | Professional Profile > Work Experience > Verify if Company field doesnt accept 4 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
112 | TD01-681 |  | Professional Profile > Work Experience > Verify if Company field doesnt accept 51 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
113 | TD01-682 |  | Professional Profile > Work Experience > Verify if Location field accepts 5 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
114 | TD01-683 |  | Professional Profile > Work Experience > Verify if Location field accepts 50 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
115 | TD01-684 |  | Professional Profile > Work Experience > Verify if Location field doesnt accept 4 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
116 | TD01-685 |  | Professional Profile > Work Experience > Verify if Location field doesnt accept 51 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
117 | TD01-686 |  | Professional Profile > Work Experience > Verify if Start Date doesnt accept a future date. | Low | Negative | Domain |  | Not executed | Failed | Failed | No | No
118 | TD01-687 |  | Professional Profile > Work Experience > Verify if In progress checkbox hides End date. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
119 | TD01-688 |  | Professional Profile > Work Experience > Verify that End date can not be before Start date. | Low | Negative | Domain |  | Not executed | Not executed | Passed | No | No
120 | TD01-689 |  | Professional Profile > Work Experience > Verify if a Work experience can be deleted. | Medium | Functional | Domain |  | Not executed | Passed | Passed | No | No
121 | TD01-690 |  | Professional Profile > Verify that can be added a Skill. | Medium | Functional | Domain |  | Not executed | Passed | Passed | No | No
122 | TD01-870 |  | Professional Profile > Verify that can not be added a Skill with no data. | Medium | Negative | Domain |  | Not executed | Passed | Passed
123 | TD01-691 |  | Professional Profile > Skills > Verify that Name field doesnt allow to save only specials characters. | Medium | Negative | Domain |  | Not executed | Not executed | Failed | No | No
124 | TD01-692 |  | Professional Profile > Verify that Skills can be deleted. | Medium | Functional | Domain |  | Not executed | Passed | Passed | No | No
125 | TD01-693 |  | Professional Profile > Skills > Verify that Name field accepts 20 Characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
126 | TD01-694 |  | Professional Profile > Skills > Verify that Name field doesnt accept 21 Characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
127 | TD01-726 |  | Professional Profile > Verify that can be added an Education. | Medium | Negative | Domain |  | Not executed | Passed | Passed | No | No
128 | TD01-727 |  | Professional Profile > Verify that can not be added an Education with empty fields. | Medium | Negative | Domain |  | Not executed | Passed | Passed | No | No
129 | TD01-728 |  | Professional Profile > Education > Verify if Institute field accepts 5 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
130 | TD01-729 |  | Professional Profile > Education > Verify if Institute field accepts 50 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
131 | TD01-730 |  | Professional Profile > Education > Verify if Institute field doesnt accept 4 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
132 | TD01-731 |  | Professional Profile > Education > Verify if Institute field doesnt accept 51 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
133 | TD01-732 |  | Professional Profile > Education > Verify if Degree field accepts 5 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
134 | TD01-733 |  | Professional Profile > Education > Verify if Degree field accepts 50 characters. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
135 | TD01-734 |  | Professional Profile > Education > Verify if Degree field doesnt accept 4 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
136 | TD01-735 |  | Professional Profile > Education > Verify if Degree field doesnt accept 51 characters. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
137 | TD01-736 |  | Professional Profile > Education > Verify that Start Date can not be a future date. | Low | Negative | Domain |  | Not executed | Not executed | Passed | No | No
138 | TD01-737 |  | Professional Profile > Education > Verify if In progress checkbox hides End date. | Low | Functional | Domain |  | Not executed | Not executed | Passed | No | No
139 | TD01-738 |  | Professional Profile > Education > Verify that End date can not be before Start date. | Low | Negative | Domain |  | Not executed | Not executed | Passed | No | No
140 | TD01-872 |  | Professional Profile > Verify that Items added can be after edited. | Low | Functional | Domain |  | Not executed | Not executed | Failed | No | No
141 | TD01-877 |  | Verify that mentor can creates a new publication with required data. | Low | Functional | Domain |  | Not executed | Passed | Passed | No | No
142 | TD01-878 |  | Verify that mentor can't create a new publication without required data. | Low | Negative | Domain |  | Not executed | Passed | Passed | No | No
143 | TD01-879 |  | Verify that General information of publication can be edited as Mentor. | Low | Functional | Domain |  | Not executed | Failed | Failed | No | No
144 | TD01-880 |  | Verify that Language and Location can be edited in a Publication as Mentor. | Low | Positive | Functional |  | Not executed | Passed | Passed | No | No
145 | TD01-881 |  | Verify that Base rates' Price per hour field doesn't accept alphabetical characters in a Publication. | Low | Negative | Domain |  | Not executed | Not executed | Failed | No | No
146 | TD01-882 |  | Verify that Base rates' Price per hour field doesn't accept negative numbers in a Publication. | Low | Negative | Domain |  | Not executed | Not executed | Failed | No | No
147 | TD01-883 |  | Verify that a Publication can be deleted as mentor. | Low | Functional | Domain |  | Not executed | Passed | Passed | No | No
148 | TD01-884 |  | Verify that Mentor receives a notification when a Student makes a proposal. | Medium | Functional | Domain |  | Passed | Passed | Passed | No | No
149 | TD01-885 |  | Verify that Student receives a notification when Mentor sends a message by Classroom chat. | Medium | Functional | Domain |  | Passed | Passed | Passed | No | No
150 | TD01-886 |  | Verify that Mentor receives a notification when Student sends a message by Classroom chat. | Medium | Functional | Domain |  | Passed | Passed | Passed | No | No
151 | TD01-887 |  | Verify that Student receives a notification when Mentor accepts a Proposal. | Medium | Functional | Domain |  | Passed | Passed | Passed | No | No
152 | TD01-888 |  | Verify that Student receives a notification when Mentor rejects a Proposal. | Medium | Functional | Domain |  | Passed | Passed | Passed | No | No

## ISSUES_FOUND
| Issue | Issue key | Team | Assignee | Severity | Blocker? | Status | Reporter | Created | Resolved | Comments
1 | My Courses > A course is not published when the visibility of the course is "private" | 368 |  |  | Medium |  | Open
2 | Languages > The "+" button replaces the original language configured. | 369 |  |  | Medium |  | In progress
3 | Languages > Not all the languages are displayed in the dropdown list when trying to add a new one | 370 |  |  | High |  | OnHold
4 | Profile > The "Studies" section only displays one study in the profile | 372 |  |  | Low |  | Open
5 | The courses that have private visibility are displayed in the profile of the mentor. | 373 |  |  | Low |  | OnHold
6 | Courses > A mentor can create a course without an email verification. | 374 |  |  | Medium |  | In progress
7 | The profile photo is uploaded by clicking the "Crop" button. | 375 |  |  | Low |  | OnHold
8 | There is no option to delete the profile photo. | 376 |  |  | Low |  | Open
9 | My Course Requests> Imentor confirms that a requested course has been created but it is not created in the background because it has not been filled with enough characters in the "Who you are looking for" field | 377 |  |  | High |  | In progress
10 | Balance> Payment methods> Paypal> When Paypal is selected as the payment method, a pop-up window opens saying "Sorry about that" | 378 |  |  | Low |  | OnHold
11 | Balance> Payment method> There is nothing to select in the payment method dropdown | 379 |  |  | Low |  | In progress
12 | Balance> Payment method> An incorrect message is shown when selecting the default value of "Payment method" | 380 |  |  | Low |  | OnHold
13 | The "Help" option does not redirect to any information. | 381 |  |  | Low |  | OnHold
14 | Classroom >Edit class> Classroom time is changed 4 hours ahead | 382 |  |  | Medium |  | In progress
15 | Mentors can rate themselves with stars in the first or second time a student's classroom is canceled. | 383 |  |  | Low |  | OnHold
16 | Chats > The expand/collapse arrow does not execute any action when the chat is selected. | 384 |  |  | Low |  | In progress
17 | GeneralProfile> Clicking the "save changes" button refreshed the page twice. | 385 |  |  | Low |  | OnHold
18 | HomePage> Subtitles recognize an interaction when the mouse hovers on them. | 386 |  |  | Medium |  | OnHold
19 | Student Profile> Can't verify email refreshing the page. | 387 |  |  | Medium |  | OnHold
20 | Chat > "Contact Support" button doesn't do anything. | 388 |  |  | High |  | Open
21 | StudentChat > Create Proposal > Main calendar doesn't allow to select days. | 389 |  |  | Medium |  | OnHold
22 | General Profile> "Date of birth" field accepts current dates. | 390 |  |  | High |  | OnHold
23 | View courses > In 'About this mentor' tab the star icons are not aligned. | 391 |  |  | Low |  | OnHold
24 | Home Page > Magnifying glass icon on search field doesn't work. | 392 |  |  | Medium |  | OnHold
25 | Sign Up > An account can´t be created with a password that contains special characters. | 393 |  |  | Medium |  | OnHold
26 | Home page > The Homepage loses its format when a resize is made to the window. | 394 |  |  | Low |  | OnHold
27 | Sign in > Error message when trying to login with google account | 395 |  |  | Medium |  | OnHold
28 | Top Rated Mentors > View Profile > Clicking on one course of the mentor shows briefly the course page. | 396 |  |  | Medium |  | Open
29 | Profile > Languages don't stay marked after making a selection. | 397 |  |  | Low |  | OnHold
30 | Publications > General Information > “Save changes” button is only enabled to save changes modifying all mandatory fields "*". | 398 |  |  | Medium |  | OnHold
31 | Publications > General Information > "Cancel" button is only enabled to cancel changes modifying all mandatory fields "*". | 399 |  |  | Low |  | OnHold
32 | Publications > Pricing > Negative numbers are accepted in Hour(s) and Price fields of PACKAGE layout as Per hour option. | 400 |  |  | Low |  | Open
33 | Publications > Pricing > Negative numbers are accepted in Price per hour field of BASE RATE layout. | 401 |  |  | Low
34 | Sign up > Data in the registration form not validating. | 402 |  |  | Medium |  | Open
35 | Sign in > There is no eye password icon to show the password. | 403 |  |  | Low |  | OnHold
36 | Sing in > Forgot password doesn’t validate the textfield. | 404 |  |  | Medium |  | OnHold
37 | Home Page > “Become a Mentor” should not be available without logging in. | 406 |  |  | Low |  | OnHold
38 | Mentor Profile > clicking on the stars is the only way to get into another mentor’s profile. | 405 |  |  | Medium |  | OnHold
39 | View Course > the user is redirected to the home page after refreshing the course or request course page. | 407 |  |  | Low |  | OnHold
40 | Profile > Data on fields of general information and socials not validated. | 408 |  |  | Low |  | OnHold
41 | Mentoring Dashboard > Pricing > Price per hour, Hour(s) and Price fields accept "e" character. |  |  |  | Low |  | OnHold
42 | Mentoring Dashboard > Fees and discounts > "Transportation fee" text moves according to length of price and gets out of EXTRA FEES layout. |  |  |  | Low |  | OnHold
43 | The site has no agreements |  |  |  | Medium |  | OnHold
44 | Profile > Socials links not validated |  |  |  | Low |  | OnHold
45 | Sign up > Weak password security policy |  |  |  | High |  | OnHold
46 | Profile > Settings > Email is still registered in database after hard delete an account. |  |  |  | High |  | OnHold
47 | Mentoring Dashboard > Is displayed an error message when clicking "Save changes" button in Language and Location, Princing and Fees and discounts tabs but information is saved. |  |  |  | Low | No | Fixed

## HISTORY_RECORD
History Record Testing
Date | Description | Comments
2023-02-09 | Exploratory test and first test execution
2023-02-13 | High-level test cases were created and second test execution | 17 high-level test cases were created
2023-02-15 | The test plan started to be writtend | We started to write the test plan to iMentor
2023-02-17 | Low-level test cases were created | 150 test cases were created
2023-02-20 | third test execution